Neighbourhood Plans – Notes from meeting with Bucks Council team

## The process

The formal stages involved in creating a neighbourhood development plan are:

- area designation: apply to Buckinghamshire Council for your neighbourhood area to be designated. This is the area in which your policies will take effect. Applications must be made by a qualifying body such as a town or parish council or a Neighbourhood Forum (if the area is unparished)

- plan preparation: the parish/town council or a neighbourhood forum produce their plan

- screening the plan: every plan needs to be screened to see if it needs a Strategic Environmental Assessment (SEA) or Habitats Regulations Assessment (HRA). Get in touch with us once you know which policies your plan will have

- pre-submission consultation: this is a minimum 6-week consultation carried out by the town or parish council or Neighbourhood Forum

- submission of the plan: the plan is checked to ensure it has the correct accompanying documents. These include a basic conditions statement, consultation statement and either a letter saying SEA/HRA are not required or an Environmental report if they were required

- submission consultation: this is a consultation like the pre-submission consultation except that it is carried out and paid for by Buckinghamshire Council. Everyone consulted in the previous consultation and everyone who responded to it is consulted again and their comments are sent to the examiner alongside the plan and its documents

- examination: the plan is examined by an independent examiner to check if it meets the basic conditions and can proceed to referendum or not. Sometimes changes are suggested

- referendum: if the plan passes an independent examination, a referendum is held and the local community votes on whether it supports the plan. If more than 50% vote ‘YES’ then it will be formally made

Contact your local planning policy team for an application form:

Adoption by the local authority:

- If the referendum is successful, the local authority formally adopts the neighbourhood plan.

Incorporation into the development plan - The adopted plan becomes part of the statutory development plan for the area and has legal force.

Implementation and Review:

- Implementation:

The parish council or neighbourhood forum may play a role in implementing the plan's policies.

- Monitoring and review:

Neighbourhood plans typically have a lifespan of around five years and should be reviewed and updated to remain relevant.

Take into account:

- Green spaces

- Building design

- Extensions

- Environmental issues

- Heritage

- Anything to protect

Define neighbourhood area:

- Parish boundary

- Settlement boundary within parish – define the different settlements

- Where countryside starts

- Open green space

Other local planning;

- Sits within County development plan and National plan

- VALP – we are a small village allowing only small scale development

- Look at policies in VALP for small villages and add detail

- Think of priorities and focus on them

Other advice

- Form group/committee with volunteers with some expertise

- Villages to look at –

Cuddington

Ashendon (Venitia)

Long crendon

Worminghall

- Can use a consultant but you don’t have to – there is a list of recommended ones

- There is a tool kit to help

- Pay attention to the conservation area